## Project Estimation
Phase | Task | Estimated Hours
Phase 1: Learning & Preparation | Learning Angular basics | 20 | 36
| Learning CQRS concepts & MediatR | 8
| Redis Caching | 8
Phase 2: Product Catalog & Add to Cart | Backend setup (.NET 8, DB Schema, EF Core) | 8 | 66
| CQRS Command/Query Handlers (MediatR) | 8
| Frontend UI setup (Angular components & layout) | 10
| Product List, Filtering, Pagination (Angular) | 16
| Add-to-Cart & Cart Management UI & Logic | 8
| Backend-Frontend Integration & Redis caching | 8
| Unit & Integration Testing | 8
Phase 3: Order Management Module | Backend Order & OrderItem Implementation | 8 | 42
| Angular Order Review & Checkout UI | 4
| Reactive Forms, Order Confirmation & History | 8
| Integration with Backend API | 4
| Validation & Stock Checking Logic | 4
| Role-based access (Admin controls) | 6
| Testing & Debugging | 8
Phase 4: Security & Authentication | OAuth 2.0 & OpenID Connect setup | 8 | 16
| API Security Measures | 4
| TLS Encryption & Azure Key Vault | 4
Phase 5: Performance Monitoring & Logging | Serilog Logging setup & Implementation | 6 | 6
Total Project Duration | Complete Project | 166