## Sheet1
Phase | Estimated Hours | Weeks
Phase 1: Learning & Preparation | 76 | 2
Phase 2: Product Catalog & Add to Cart | 116 | 3
Phase 3: Order Management Module | 84 | 2
Phase 4: Security & Authentication | 36 | 1
Phase 5: Performance Monitoring & Logging | 32 | 1
Total Project Duration | 344 | 9